## Master Gap Analysis
NPI DOCTOR NOTIFICATION SYSTEM — COMPLETE GAP ANALYSIS
PDF Requirements (ProMed Medical Supplies, June 2026) vs Current ClaimLens Build
# | Feature / Requirement (from PDF) | What PDF Requires (exact spec) | PDF Section | Status | Gap / What's Missing | Priority | Phase
PHASE 1 — Foundation (Weeks 1–3)
1 | Database: PHYSICIAN table | npi PK, first/last name, specialty, taxonomy, practice_name, practice_address (JSONB), email_primary, email_secondary, mobile_phone, notification_mode, alert_threshold, vendor_type_filter (JSONB), whitelisted_vendors (JSONB), auto_escalate_hours, verified, verification_method, registered_date, last_login | Sec 9 | ⚠️ Partial | Physician table exists but missing: notification_mode, alert_threshold, vendor_type_filter, whitelisted_vendors, auto_escalate_hours columns. These are needed for trigger engine filtering. | 🔴 Critical | Phase 1
2 | Database: CLAIM_NOTIFICATION table | notification_id, claim_number, physician_npi, physician_npi_role (ORDERING/REFERRING/CERTIFYING/ATTENDING), vendor_npi, vendor_name, vendor_type, patient_mbi, patient_name_partial (masked J*** S***), dos_from, dos_to, service_description, hcpcs_codes (JSONB), amount_billed, amount_paid, era_file_id, notification_sent_at, email_sent, push_sent, sms_sent, status, physician_response, response_at, response_changed, response_change_reason, response_changed_at, escalated_at, created_at | Sec 9 | ❌ Not Built | Table does not exist at all. This is the core table the entire notification system writes to. Must be built before any other Phase 2 work. | 🔴 Critical | Phase 1
3 | Database: DISPUTE_CASE table | case_id, notification_id FK, physician_npi FK, vendor_npi, dispute_type (DISPUTE/FRAUD_REPORT), physician_notes, billing_provider_notified_at, response_due_date, provider_response_type, medicare_response_proof (JSONB), vendor_response, vendor_docs (JSONB), vendor_responded_at, reminder_sent_day7, reminder_sent_day13, status, compliance_reviewer, oig_referral_date, oig_case_number, opened_at, closed_at, resolution_notes | Sec 9 | ❌ Not Built | Table does not exist. The current 'actions' table records physician actions but has no dispute case lifecycle (15-day window, vendor response, OIG referral tracking). | 🔴 Critical | Phase 1
4 | Database: PREAUTH_REQUEST table | preauth_id, physician_npi FK, vendor_npi, patient_mbi, patient_name, service_description, hcpcs_code, estimated_amount, status (PENDING/APPROVED/DENIED), physician_response, response_at, preauth_token (UNIQUE), expires_at, created_at | Sec 9 | ❌ Not Built | Table does not exist. Pre-auth is listed as Optional Add-On (Phase 7) so lower priority, but schema should be created now. | 🟡 Medium | Phase 7
5 | NPPES NPI Registry integration | Real-time lookup: auto-populate name, specialty, address on NPI entry during registration. npiregistry.cms.hhs.gov/api — no auth required. | Sec 11 | ⚠️ Partial | NPPES lookup exists but mocked in dev. Config flags exist to wire in live API. Must be activated before pilot launch. | 🟠 High | Phase 1
6 | Physician Registration — 5-step onboarding flow | Step 1: Enter NPI + auto-populate. Step 2: Identity verification (ID.me / PECOS / DEA+License / Email OTP / Manual). Step 3: Contact preferences. Step 4: Notification rules. Step 5: Review & Activate. | Sec 4 | ⚠️ Partial | Registration and auth exist. Identity verification mocked. Steps 3-4 (notification preferences and rules) not wired to DB columns that don't exist yet. | 🟠 High | Phase 1
7 | Auth: MFA + JWT + role-based access | Auth0 or AWS Cognito recommended. Physician, Physician Office Admin, Vendor, Compliance Officer, System Admin roles. MFA required for PHI access. | Sec 13 | ✅ Built | JWT + bcrypt + TOTP MFA built. Roles: physician and plan_investigator. Need to add: vendor, compliance_officer, system_admin, physician_office_admin roles. | 🟡 Medium | Phase 1
PHASE 2 — 835 Parser + Trigger Engine (Weeks 4–6)
8 | 835 ERA File Parser | Parse EDI 835 files using pyx12 (Python). Extract: NM1*DK = Ordering NPI, NM1*DN = Referring NPI, NM1*82 = Rendering NPI, NM1*77 = Vendor NPI+name, CLP = claim number + billed + paid, SVC = HCPCS codes, DTM = service dates, NM1*QC = patient name (mask to J*** S***). Handle multiple claim loops per file. | Sec 2.3 | ❌ Not Built | backend/parsers/era_835.py does not exist. pyx12 not installed. No EDI parsing capability at all. This is the single most critical missing piece. | 🔴 Critical | Phase 2
9 | NPI Extraction — all 4 roles | Every inbound 835 must extract NPIs from 4 roles: ORDERING (NM1*DK), REFERRING (NM1*DN), CERTIFYING (Plan of Care), ATTENDING (Hospice NOE). Each role is an independent trigger point. | Sec 2.1 | ❌ Not Built | No NPI role extraction exists. Current system uses a single NPI per claim. PDF requires checking all 4 roles independently, each triggering a separate notification. | 🔴 Critical | Phase 2
10 | Patient Name Masking | Patient name in all notifications must be masked: 'John Smith' → 'J*** S***'. Full name only visible in secure portal after authenticated login. Patient MBI must never appear in email subject or push previews. | Sec 13.1 | ❌ Not Built | No masking helper exists. Current system displays full patient names. HIPAA violation risk if not implemented before any real data. | 🔴 Critical | Phase 2
11 | Trigger Engine — processIncomingClaim() | Loop over all 4 NPI roles per claim. For each non-null NPI: lookup physician registry → check verified=TRUE → apply physician preference filters → create ClaimNotification(PENDING) → queue for notification send. | Sec 5.1 | ❌ Not Built | backend/triggers/engine.py does not exist. The trigger logic that connects 835 parsing to notification creation is entirely missing. | 🔴 Critical | Phase 2
12 | Physician Preference Filtering | Before creating notification, check: notify_new_vendors_only (skip if vendor seen before), alert_threshold (skip if amount below), vendor_type_filter (skip if vendor type not in filter), whitelisted_vendors (skip if vendor pre-approved), digest_mode (hold for batch if not real-time). | Sec 5.2 | ❌ Not Built | No preference filtering logic exists. The DB columns for preferences don't exist yet either (see Phase 1 gap). Both must be built together. | 🔴 Critical | Phase 2
13 | Auto-Escalation Rules (6 conditions) | Regardless of physician prefs, auto-escalate if: (1) NPI used by 3+ vendors in same week → URGENT, (2) Claim >$10K from new vendor → HIGH, (3) Patient in different state from physician → MEDIUM, (4) Previously disputed vendor bills again → CRITICAL, (5) Vendor NPI on OIG exclusion list → skip physician, escalate directly → CRITICAL, (6) Same patient billed for hospice + home health simultaneously → HIGH. | Sec 5.3 | ⚠️ Partial | ClaimLens has 16 fraud rules including OIG hit, geographic anomaly, cross-NPI supplier. But these run on batch data not in real-time per-claim trigger. Must be rewired into trigger engine as real-time checks. | 🔴 Critical | Phase 2
14 | Notification Queue — DB-based | ClaimNotification records with status=PENDING form the queue. get_pending_notifications(), mark_notification_queued(), escalate_stale_notifications() (cron job finds PENDING older than auto_escalate_hours and sets ESCALATED). No Redis/Celery needed for Phase 2. | Sec 5 | ❌ Not Built | No notification queue exists. Current SSE system pushes live but has no persistent queue with state management (PENDING → QUEUED → SENT → ESCALATED). | 🔴 Critical | Phase 2
15 | Claim Ingestion API — POST /api/v1/claims/ingest | Accepts multipart 835 EDI file upload. Parses with era_835.py. Runs each claim through trigger engine. Returns count of notifications created. | Sec 10.2 | ❌ Not Built | Endpoint does not exist. | 🔴 Critical | Phase 2
16 | Claim Ingestion API — POST /api/v1/claims/ingest/single | Accepts single claim as JSON body. Validates fields. Runs through trigger engine. Returns created notification record. | Sec 10.2 | ❌ Not Built | Endpoint does not exist. | 🔴 Critical | Phase 2
17 | Webhook — POST /api/v1/webhooks/era | Clearinghouse webhook endpoint (no standard auth — uses webhook secret header). Same processing as /ingest but designed for Availity / Change Healthcare / Waystar push delivery. | Sec 10.5 | ❌ Not Built | Endpoint does not exist. | 🔴 Critical | Phase 2
18 | Webhook — POST /api/v1/webhooks/claim-status | Receive 277 claim status updates from clearinghouse. | Sec 10.5 | ❌ Not Built | Endpoint does not exist. | 🟡 Medium | Phase 2
19 | GET /api/v1/webhooks/health | Webhook health check endpoint. | Sec 10.5 | ❌ Not Built | Endpoint does not exist. | 🟢 Low | Phase 2
20 | GET /api/v1/claims/{claim_number} | Return claim with its full notification status. | Sec 10.2 | ❌ Not Built | Endpoint does not exist. | 🟠 High | Phase 2
21 | GET /api/v1/notifications/pending | Returns all pending (unresponded) notifications. Used by Phase 3 sender and by compliance reviewers. | Sec 10.2 | ❌ Not Built | Endpoint does not exist. | 🔴 Critical | Phase 2
22 | Physician Preferences API — GET/PUT /api/v1/physicians/{npi}/preferences | GET: return current notification settings. PUT: update notification_mode, alert_threshold, vendor_type_filter, whitelisted_vendors, auto_escalate_hours. | Sec 10.1 | ❌ Not Built | Endpoints do not exist. Underlying DB columns also missing. | 🔴 Critical | Phase 2
23 | PUT /api/v1/physicians/{npi}/whitelist | Add/remove pre-approved vendors from physician's whitelist. | Sec 10.1 | ❌ Not Built | Endpoint does not exist. | 🟠 High | Phase 2
PHASE 3 — Email + Push Notifications (Weeks 7–8)
24 | SendGrid Email — Physician NPI Alert | FROM: alerts@npiwatch.com. SUBJECT: [NPI Alert] Your NPI was used on a Medicare claim — Action Required. Body: exact template per PDF Sec 6.1 with vendor info, masked patient, HCPCS codes, billed/paid amounts, NPI role. Three one-click buttons: CONFIRM / DISPUTE / REPORT FRAUD (no login required — tokenized links). | Sec 6.1 | ❌ Not Built | No email notification system. No SendGrid integration. No tokenized one-click response links. This is the core product loop. | 🔴 Critical | Phase 3
25 | Public response endpoint — GET /respond?token=xxx&action=CONFIRM | Physician clicks email button without logging in. Token validates which notification + which physician. Records response. Redirects to portal with confirmation message. | Sec 7.1 | ❌ Not Built | No public tokenized response endpoint exists. Without this, email buttons have nowhere to go. | 🔴 Critical | Phase 3
26 | Firebase FCM Push Notification | Title: 'NPI Alert — Action Required'. Body: '[Vendor] used your NPI for a $X claim. Tap to review.' Deep link to claim detail. Badge count increment. CONFIRM ¦ DISPUTE actions without opening app. High priority / urgent tone for CRITICAL flags. | Sec 6.2 | ❌ Not Built | No Firebase integration. No push notification capability. | 🔴 Critical | Phase 3
27 | Apple APNs (iOS push) | iOS push certificates required. Same content as FCM. Bypasses Do Not Disturb for CRITICAL flags. | Sec 6.2 | ❌ Not Built | No APNs integration. | 🟠 High | Phase 3
28 | Twilio SMS — fallback notification | 160-char template: 'NPI ALERT: Your NPI was used by [Vendor] for a $X Medicare claim. Reply CONFIRM, DISPUTE, or call 1-800-NPI-WATCH. Ref: CLM-XXXXXX' | Sec 6.3 | ❌ Not Built | No Twilio integration. | 🟡 Medium | Phase 3
29 | Notification delivery tracking | Per notification: email_sent (bool), push_sent (bool), sms_sent (bool), notification_sent_at (timestamp). Failed delivery → retry logic → fallback to next channel. | Sec 9 | ❌ Not Built | Fields exist in the PDF schema for CLAIM_NOTIFICATION but the table and tracking logic don't exist yet. | 🟠 High | Phase 3
30 | Vendor rejection email — 15-day notice | Immediate email to vendor on physician DISPUTE. Subject: '[URGENT] Physician Rejected Claim #XXX — 15-Day Response Required'. Body: exact template per PDF Sec 7.3 with claim details, 15-day deadline, upload button, view case button. | Sec 7.3 | ❌ Not Built | No vendor notification system. Vendor email/contact not stored. No rejection notice sent currently. | 🔴 Critical | Phase 3
31 | Day 7 + Day 13 reminder emails to vendor | Automated reminders at Day 7 and Day 13 after physician dispute. reminder_sent_day7 and reminder_sent_day13 flags on DISPUTE_CASE track whether sent. | Sec 7.3 | ❌ Not Built | No reminder system. Cron job needed. | 🟠 High | Phase 3
PHASE 4 — Physician Web Portal (Weeks 9–11)
32 | Screen 2: Physician Dashboard | Notification counter by status (Pending/Confirmed/Disputed/Fraud Reported). Recent activity feed — last 10 notifications with vendor name, amount, status badge. Quick stats: total NPI claims this month, confirmed, disputed. URGENT/CRITICAL alert banner. 'Review Pending Notifications' button. | Sec 12 | ⚠️ Partial | Physician dashboard exists but shows ClaimLens fraud analytics (risk scores, leaderboard). PDF wants a notification-centric dashboard. Needs to be redesigned around claim_notifications table which doesn't exist yet. | 🔴 Critical | Phase 4
33 | Screen 3: Notification Detail — Claim Review | Vendor info card (name, type, NPI, address, Medicare enrollment status). Claim info card (masked patient, dates, service description, HCPCS codes). Amount block (billed/approved/paid). NPI role on this claim. Action buttons: CONFIRM (green) ¦ DISPUTE (orange) ¦ REPORT FRAUD (red). Optional notes field. Countdown timer to auto-escalation. | Sec 12 | ⚠️ Partial | Claim detail view exists with confirm/dispute actions. Missing: NPI role display, vendor info card, Medicare enrollment status, countdown timer, REPORT FRAUD button (only CONFIRM and DISPUTE exist), optional notes field. | 🟠 High | Phase 4
34 | Screen 5: Notification History | Full searchable list of all past notifications. Filter by: vendor name, vendor type, date range, status, amount. Export: CSV or PDF. Audit trail: full log of all actions on each notification. | Sec 12 | ❌ Not Built | Notification history screen does not exist (claim_notifications table doesn't exist yet). The current claims table shows claims, not notification events. | 🟠 High | Phase 4
35 | GET /api/v1/physicians/{npi}/notifications | List all notifications for physician (paginated). | Sec 10.1 | ❌ Not Built | Endpoint does not exist. | 🔴 Critical | Phase 4
36 | GET /api/v1/physicians/{npi}/notifications/stats | Summary counts by status (PENDING, CONFIRMED, DISPUTED, FRAUD_REPORTED, ESCALATED). | Sec 10.1 | ❌ Not Built | Endpoint does not exist. | 🟠 High | Phase 4
37 | GET /api/v1/notifications/{id} | Get full notification detail. | Sec 10.2 | ❌ Not Built | Endpoint does not exist. | 🔴 Critical | Phase 4
38 | POST /api/v1/notifications/{id}/respond | Physician response: CONFIRM / DISPUTE / FRAUD_REPORTED. Triggers downstream: vendor notification on DISPUTE, OIG escalation on FRAUD, compliance queue on no-response. | Sec 10.2 | ⚠️ Partial | POST /actions exists for in-app responses. But not wired to CLAIM_NOTIFICATION table, no vendor notification triggered on DISPUTE, no OIG package on FRAUD_REPORTED. | 🔴 Critical | Phase 4
39 | POST /api/v1/notifications/{id}/resend | Resend notification to physician (email/push/SMS). | Sec 10.2 | ❌ Not Built | Endpoint does not exist. | 🟡 Medium | Phase 4
40 | POST /api/v1/notifications/{id}/change-response | Physician changes DISPUTE → CONFIRM within 15-day window. Must validate: status==DISPUTED AND daysSinceDispute <= 15. Logs as distinct event with reason. Notifies vendor. Closes dispute case. | Sec 7.4 | ❌ Not Built | Endpoint does not exist. changeResponse() pseudocode defined in PDF — exact logic must be implemented. | 🟠 High | Phase 4
PHASE 5 — Mobile App (Weeks 12–14)
41 | React Native iOS + Android app | Full physician mobile app. Push notification integration. One-tap CONFIRM / DISPUTE actions from notification (without opening app). Deep link to claim detail. | Sec 14.1 | ❌ Not Built | No mobile app exists. React Native not started. | 🟡 Medium | Phase 5
PHASE 6 — Dispute & Case Management (Weeks 15–16)
42 | 15-Day Dispute Workflow Engine | Day 0: Physician disputes → vendor notified immediately → case opened → 15-day clock starts. Day 7: reminder to vendor. Day 13: final reminder. Day 15: if no response → NON_RESPONSIVE → auto-escalate to CMS/compliance. Day 30: CMS RAC audit referral. | Sec 7.2 | ❌ Not Built | Dispute workflow is the most complex missing piece. Current system records a dispute action but stops there. No timeline engine, no vendor notifications, no auto-escalation at Day 15. | 🔴 Critical | Phase 6
43 | Screen 4: Dispute Case Management portal | Open cases list with days-remaining counter. Case detail with full claim info + physician notes + vendor uploaded docs. Inline PDF/image viewer. Resolution actions: Accept Docs / Maintain Dispute / Escalate. OIG Referral one-click PDF generator. | Sec 12 | ❌ Not Built | Screen does not exist. | 🔴 Critical | Phase 6
44 | GET /api/v1/disputes | List all dispute cases (filterable by status, physician, vendor, date). | Sec 10.3 | ❌ Not Built | Endpoint does not exist. | 🔴 Critical | Phase 6
45 | GET /api/v1/disputes/{case_id} | Get full dispute case detail. | Sec 10.3 | ❌ Not Built | Endpoint does not exist. | 🔴 Critical | Phase 6
46 | POST /api/v1/disputes/{case_id}/vendor-response | Vendor submits documentation (upload proof files). | Sec 10.3 | ❌ Not Built | Endpoint does not exist. | 🔴 Critical | Phase 6
47 | POST /api/v1/disputes/{case_id}/medicare-response | Provider logs proof they responded to Medicare directly: claim number, date submitted, supporting docs. | Sec 10.3 | ❌ Not Built | Endpoint does not exist. | 🔴 Critical | Phase 6
48 | GET /api/v1/disputes/{case_id}/deadline | Returns days remaining on 15-day provider response window. | Sec 10.3 | ❌ Not Built | Endpoint does not exist. | 🟠 High | Phase 6
49 | POST /api/v1/disputes/{case_id}/close | Compliance officer closes a case with resolution notes. | Sec 10.3 | ❌ Not Built | Endpoint does not exist. | 🟠 High | Phase 6
50 | POST /api/v1/disputes/{case_id}/refer-oig | Generate OIG referral and mark case as REFERRED_OIG. Must NOT auto-submit — requires compliance staff human review gate. | Sec 10.3 | ❌ Not Built | Endpoint does not exist. CRITICAL legal note: must have human review gate per PDF Sec 13.2. | 🔴 Critical | Phase 6
51 | GET /api/v1/disputes/{case_id}/oig-package | Download generated OIG referral package as PDF. Auto-generates referral package with all claim details, physician response, timeline. | Sec 10.3 | ❌ Not Built | Endpoint does not exist. PDF generator not built. | 🔴 Critical | Phase 6
PHASE 7 — Vendor Portal (Weeks 17–18)
52 | Screen 6: Vendor Dashboard | Claim status board: all submitted claims with physician confirmation status (CONFIRMED/PENDING/DISPUTED/FRAUD REPORTED). Physician response rate / trust score. Dispute center with deadline counters + doc upload. Pre-auth request form. Physician onboarding invite tool. Audit package generator for confirmed claims. | Sec 8.1 | ❌ Not Built | No vendor portal exists. Vendor role not in current auth system. | 🟡 Medium | Phase 7
53 | Pre-Authorization Flow (Optional Add-On) | Vendor sends pre-auth request before billing. Physician receives notification to APPROVE/DENY. If APPROVED: preauth_token generated, auto-confirms when ERA received. If DENIED: vendor blocked from billing that patient/service, denial logged, fraud flag if they bill anyway. | Sec 8.2 | ❌ Not Built | No pre-auth system exists. | 🟢 Low | Phase 7
54 | POST /api/v1/preauth/request | Vendor creates pre-auth request. | Sec 10.4 | ❌ Not Built | Endpoint does not exist. | 🟢 Low | Phase 7
55 | GET /api/v1/preauth/{preauth_id} | Get pre-auth status. | Sec 10.4 | ❌ Not Built | Endpoint does not exist. | 🟢 Low | Phase 7
56 | POST /api/v1/preauth/{preauth_id}/respond | Physician approves or denies pre-auth. | Sec 10.4 | ❌ Not Built | Endpoint does not exist. | 🟢 Low | Phase 7
57 | GET /api/v1/preauth/validate/{token} | Validate pre-auth token on claim submission. | Sec 10.4 | ❌ Not Built | Endpoint does not exist. | 🟢 Low | Phase 7
PHASE 8 — Testing + HIPAA Audit (Weeks 19–20)
58 | HIPAA: PHI minimization in notifications | Patient name masked in all email/push (J*** S***). MBI never in email subject or push preview. Full name only in secure portal after auth. | Sec 13.1 | ❌ Not Built | No masking implemented anywhere. HIPAA risk. | 🔴 Critical | Phase 8
59 | HIPAA: AES-256 at rest + TLS 1.3 in transit | All data encrypted at rest. TLS 1.3 minimum for all connections. | Sec 13.1 | ❌ Not Built | Localhost only. No production encryption configured. | 🔴 Critical | Phase 8
60 | HIPAA: MFA for PHI access | Physician portal requires MFA before PHI is accessible. | Sec 13.1 | ✅ Built | TOTP MFA and Email OTP built and working. | ✅ Done | Phase 8
61 | HIPAA: Audit logs — 6 year retention | All PHI access must be logged with timestamp, user, action. Retained 6 years. | Sec 13.1 | ❌ Not Built | No HIPAA-compliant audit log system. Current logs are dev logs only. | 🔴 Critical | Phase 8
62 | BAA with: SendGrid, Twilio, Firebase, cloud host, clearinghouse | Signed Business Associate Agreements required with all third-party services that touch PHI before launch. | Sec 13.1 | ❌ Not Built | No third-party services integrated yet. BAAs needed before any real data. | 🔴 Critical | Phase 8
63 | Legal: No auto-submit OIG referrals | Auto-generated OIG packages must be reviewed by compliance staff before submission. System must enforce human review gate. | Sec 13.2 | ❌ Not Built | No OIG system exists yet. When built must include mandatory human review step. | 🔴 Critical | Phase 8
64 | Legal: Physician consent for data sharing | Physicians and vendors must authorize data sharing via signed consent. App does NOT have direct CMS data access — processes 835 files that providers share. | Sec 13.2 | ❌ Not Built | No consent capture in registration flow. | 🔴 Critical | Phase 8
EXTERNAL INTEGRATIONS (PDF Section 11)
65 | NPPES NPI Registry — real-time lookup | npiregistry.cms.hhs.gov/api — no auth. Real-time on registration and claim parsing. | Sec 11 | ⚠️ Partial | Mocked in dev. Config flag exists to enable live. | 🟠 High | Phase 1
66 | OIG LEIE Exclusion List — monthly sync | oig.hhs.gov/exclusions — monthly bulk download. Cross-check vendor NPI before notification trigger. | Sec 11 | ⚠️ Partial | OIG lookup exists in ClaimLens rules but as a static seed, not a monthly sync. | 🟠 High | Phase 2
67 | CMS PECOS — weekly enrollment verification | pecos.cms.gov — weekly sync. Verify physician has active Medicare enrollment. | Sec 11 | ❌ Not Built | PECOS integration mocked. No weekly sync. | 🟡 Medium | Phase 8
68 | Medicare 835 ERA — clearinghouse integration | Availity / Change Healthcare / Waystar. Daily or real-time. Primary claim data source. Needs clearinghouse API key. | Sec 11 | ❌ Not Built | No clearinghouse integration. Only manual file upload endpoint (which also doesn't exist yet). | 🔴 Critical | Phase 2
69 | SendGrid / AWS SES — HIPAA-compliant email | API key required. BAA with provider required. | Sec 11 | ❌ Not Built | No email service integrated. | 🔴 Critical | Phase 3
70 | Firebase FCM + Apple APNs | Firebase project + Apple Developer account + certs required. | Sec 11 | ❌ Not Built | No push notification service integrated. | 🟠 High | Phase 3
71 | Twilio SMS | Twilio account + API key required. | Sec 11 | ❌ Not Built | No SMS service integrated. | 🟡 Medium | Phase 3
72 | ID.me / Login.gov — identity verification | OAuth 2.0. Recommended for high-security physician identity verification. | Sec 11 | ❌ Not Built | Identity verification mocked. | 🟡 Medium | Phase 8
73 | AWS S3 — file storage | 835 files, vendor dispute documents, OIG packages. HIPAA BAA available from AWS. | Sec 14.1 | ❌ Not Built | No file storage. All files would be local which is not production-ready. | 🟠 High | Phase 6
BUILT BUT NOT IN PDF — Extra Features
74 | Plan Investigator portal | N/A — not in PDF | Not in PDF | 🔄 Extra (Not in PDF) | Built as ClaimLens fraud analytics. PDF only has Compliance Officer role with dispute review. This is a superset — keep but not part of MVP. | Info only | Extra
75 | NPI Risk Leaderboard + Fraud Scoring (0-100) | N/A — not in PDF | Not in PDF | 🔄 Extra (Not in PDF) | Valuable analytics layer but not what client asked for in this PDF. Phase 2+ enhancement once core notification loop is built. | Info only | Extra
76 | 16 Fraud Detection Rules (SQL) | N/A — not in PDF | Not in PDF | 🔄 Extra (Not in PDF) | PDF only requires 6 auto-escalation triggers (Sec 5.3). The 16 rules are a superset — reuse the OIG, geo-anomaly, and duplicate rules as escalation triggers in the new engine. | Info only | Extra
77 | SSE Real-time alerts to plan investigator | N/A — not in PDF | Not in PDF | 🔄 Extra (Not in PDF) | SSE infrastructure is reusable for real-time notification delivery. Redirect the SSE stream to physician portal notifications. | Info only | Extra
78 | Supplier Watchlist | N/A — not in PDF | Not in PDF | 🔄 Extra (Not in PDF) | Vendor watchlist concept overlaps with PDF's vendor dispute center. Partially reusable. | Info only | Extra

## API Endpoints Checklist
API ENDPOINTS — PDF vs Current Build (Complete Checklist)
Every endpoint defined in PDF Section 10. Green = exists. Red = must build.
# | Method | Endpoint | PDF Section | Status | Notes
Physician Endpoints
1 | POST | /api/v1/physicians/register | 10.1 | ⚠️ Partial | Registration exists but missing preference steps 3-4
2 | POST | /api/v1/physicians/verify | 10.1 | ⚠️ Partial | Verify flow exists but mocked
3 | GET | /api/v1/physicians/{npi}/profile | 10.1 | ✅ Built | Profile endpoint exists
4 | PUT | /api/v1/physicians/{npi}/profile | 10.1 | ⚠️ Partial | Update exists but missing notification preference fields
5 | PUT | /api/v1/physicians/{npi}/whitelist | 10.1 | ❌ Not Built | Whitelist management not built
6 | GET | /api/v1/physicians/{npi}/notifications | 10.1 | ❌ Not Built | claim_notifications table doesn't exist yet
7 | GET | /api/v1/physicians/{npi}/notifications/stats | 10.1 | ❌ Not Built | Stats by status not built
Notification Endpoints
8 | GET | /api/v1/notifications/{id} | 10.2 | ❌ Not Built | Notification detail endpoint missing
9 | POST | /api/v1/notifications/{id}/respond | 10.2 | ⚠️ Partial | POST /actions exists but not wired to claim_notifications or vendor alerts
10 | POST | /api/v1/notifications/{id}/resend | 10.2 | ❌ Not Built | Resend not built
11 | GET | /api/v1/notifications/pending | 10.2 | ❌ Not Built | Pending queue endpoint missing
12 | POST | /api/v1/claims/ingest | 10.2 | ❌ Not Built | 835 file ingestion — core missing endpoint
13 | POST | /api/v1/claims/ingest/single | 10.2 | ❌ Not Built | Single claim JSON ingestion missing
14 | GET | /api/v1/claims/{claim_number} | 10.2 | ❌ Not Built | Claim + notification status lookup missing
Dispute & Case Endpoints
15 | GET | /api/v1/disputes | 10.3 | ❌ Not Built | Dispute list endpoint missing
16 | GET | /api/v1/disputes/{case_id} | 10.3 | ❌ Not Built | Dispute detail missing
17 | POST | /api/v1/disputes/{case_id}/vendor-response | 10.3 | ❌ Not Built | Vendor doc upload missing
18 | POST | /api/v1/disputes/{case_id}/medicare-response | 10.3 | ❌ Not Built | Medicare response logging missing
19 | POST | /api/v1/notifications/{id}/change-response | 10.3 | ❌ Not Built | DISPUTE → CONFIRM change flow missing
20 | GET | /api/v1/disputes/{case_id}/deadline | 10.3 | ❌ Not Built | 15-day countdown missing
21 | POST | /api/v1/disputes/{case_id}/close | 10.3 | ❌ Not Built | Case closure missing
22 | POST | /api/v1/disputes/{case_id}/refer-oig | 10.3 | ❌ Not Built | OIG referral trigger missing
23 | GET | /api/v1/disputes/{case_id}/oig-package | 10.3 | ❌ Not Built | OIG package PDF download missing
Pre-Authorization Endpoints
24 | POST | /api/v1/preauth/request | 10.4 | ❌ Not Built | Pre-auth not built (Phase 7 — lower priority)
25 | GET | /api/v1/preauth/{preauth_id} | 10.4 | ❌ Not Built | Pre-auth status not built
26 | POST | /api/v1/preauth/{preauth_id}/respond | 10.4 | ❌ Not Built | Physician pre-auth response not built
27 | GET | /api/v1/preauth/validate/{token} | 10.4 | ❌ Not Built | Token validation not built
Webhook Endpoints
28 | POST | /api/v1/webhooks/era | 10.5 | ❌ Not Built | Clearinghouse webhook — core missing
29 | POST | /api/v1/webhooks/claim-status | 10.5 | ❌ Not Built | 277 status update webhook missing
30 | GET | /api/v1/webhooks/health | 10.5 | ❌ Not Built | Webhook health check missing

## Summary Scorecard
BUILD SCORECARD — NPI Notification System
Phase | Total Items | Built ✅ | Not Built ❌ | Next Action
Phase 1 — Foundation | 8 | 3 | 5 | Add notification preference columns to physician table. Add claim_notifications, dispute_case, preauth tables.
Phase 2 — 835 Parser + Engine | 13 | 0 | 13 | Start here. Generate synthetic 835. Build era_835.py parser. Build trigger engine. Build ingestion APIs.
Phase 3 — Notifications | 8 | 0 | 8 | SendGrid + Firebase + Twilio. One-click tokenized response links. Vendor rejection emails.
Phase 4 — Physician Portal | 8 | 2 | 6 | Redesign dashboard around claim_notifications. Add notification history screen. Wire /respond to new tables.
Phase 5 — Mobile App | 1 | 0 | 1 | React Native app. Lowest immediate priority.
Phase 6 — Dispute Mgmt | 9 | 0 | 9 | 15-day workflow engine. Dispute case screens. OIG referral generator with human review gate.
Phase 7 — Vendor Portal | 5 | 0 | 5 | Vendor registration + dashboard + pre-auth. Phase 7 per timeline.
Phase 8 — HIPAA / Launch | 6 | 1 | 5 | PHI masking everywhere. Audit logs. BAA with all vendors. Pen test. Legal review of OIG flow.
External Integrations | 8 | 1 | 7 | SendGrid + Firebase + Twilio + Clearinghouse + S3 + ID.me + PECOS.
Extra (Not in PDF) | 5 | 5 | 0 | Keep — reuse fraud rules as escalation triggers. Redirect SSE to physician notifications.
TOTAL | 71 | 12 | 59
Overall completion: 12 of 71 items built (16.9% done vs PDF requirements)
IMMEDIATE NEXT STEPS — DO THESE FIRST
1. DB MIGRATION — Add: notification_mode, alert_threshold, vendor_type_filter, whitelisted_vendors, auto_escalate_hours to physician/users table. Create claim_notifications table (exact schema from PDF Sec 9). Create dispute_cases table.
2. 835 PARSER — Install pyx12. Build backend/parsers/era_835.py. Generate synthetic 835 EDI file (5 scenarios). Test extraction of all 4 NPI roles.
3. TRIGGER ENGINE — Build backend/triggers/engine.py. Implement processIncomingClaim(). Wire existing OIG/geo-anomaly rules into real-time escalation checks.
4. INGESTION APIS — POST /api/v1/claims/ingest, POST /api/v1/claims/ingest/single, POST /api/v1/webhooks/era.
5. SENDGRID EMAIL — Exact template from PDF Sec 6.1. Tokenized one-click CONFIRM/DISPUTE/FRAUD links. Public /respond endpoint (no login required).
6. VENDOR REJECTION EMAIL — On DISPUTE, immediately send formal 15-day notice to vendor per PDF Sec 7.3 template.
7. PHI MASKING — Patient name → J*** S*** everywhere in emails/push. MBI never in subject lines. HIPAA blocker for real data.